# Plan of Approach

Project title: Improving the realism and usability of an existing FEM breast model for AI training applications
Student: Daan Kuijpers
Period: 31-3-2026/12-7-2026
Supervisor CZE: Coen Hurkmans
University supervisor – TU/e: Wouter Huberts

## 1. Project Description / Introduction

Breast cancer remains the most common cancer among women worldwide. Early detection significantly improves survival rates, but current screening methods such as X-ray mammography have important limitations. Mammography sensitivity decreases in women with dense breast tissue, making it less suitable for younger women, and it exposes patients to ionizing radiation (von Euler-Chelpin, 2019; Teixeira, 2023).

A promising radiation-free alternative is based on multi-camera imaging combined with biomechanical breast modeling. In this approach, the biomechanical model is not the diagnostic tool itself, but serves as a simulation environment to support and validate the imaging pipeline. It enables researchers to simulate how breast tissue deforms under gravity and motion, providing realistic reference data for training and validating neural networks for cancer detection.

Finite element models (FEM) play a key role in simulating breast deformation and evaluating this imaging concept. Initial FEM breast models assumed homogeneous tissue properties, which oversimplified the mechanical behavior of the breast. More recently, these models have been extended to include heterogeneous tissue properties (Graduation project Ryan Engels), resulting in improved biomechanical realism. However, important limitations remain, particularly in the geometric representation and anatomical variability of the model. Current implementations often rely on simplified, axisymmetric geometries and idealized internal structures, which do not fully capture the complexity and variability of real breast anatomy. In reality, breasts consist of adipose and glandular tissues with distinct material properties and highly irregular spatial distributions (Galbreath & Goswami, 2025).

This project therefore focuses on further improving the anatomical realism of an existing FEM breast model by enhancing geometric representation and refining the glandular structure. The aim is to evaluate how these improvements influence simulated deformation behavior, thereby contributing to a more realistic and robust model that can be used for generating synthetic data for AI-based, radiation-free breast cancer detection.

## 2. Objective

The objective of this project is to improve the anatomical and biomechanical realism of an existing FEM breast model, building on a previously developed heterogeneous model, by enhancing geometry representation and glandular structure, and evaluating their impact on simulated deformation behavior.

Research question:
How do controlled variations in breast geometry and glandular distribution influence displacement and stress patterns in a heterogeneous FEM breast model?

Specific aims:

- Analyze limitations of the existing heterogeneous FEM model

- Improve breast geometry beyond axisymmetric approximation

- Refine glandular structure representation

- Evaluate impact on displacement and stress patterns

## 3. Scope

This project focuses on improving the realism and usability of an existing FEM breast model, with an emphasis on geometry and anatomical representation.

In scope:

- Analysis of the existing FEM pipeline implemented in the graduation report from Ryan Engels

- Improvement of breast geometry beyond the current axisymmetric approximation

- Implementation of geometric variation and asymmetry

- Refinement of glandular structure representation

- FEM simulations and comparison of biomechanical outputs (displacement, stress)

Out of scope:

- Development of a completely new FEM pipeline

- Full anatomical modeling (e.g. muscles, ligaments, rib cage)

- Clinical validation or use of patient-specific data

- Development or training of AI models

## 4. Approach (Methods & Materials)

### 4.1 Analysis of Existing Model

The project starts with a detailed analysis of the existing FEM breast model. This includes evaluation of:

- Geometry generation (axisymmetric model)

- Meshing approach (e.g. in Teixeira,2023)

- Material definitions and heterogeneity implementation

- Simulation setup in FEBio

The goal is to identify key limitations that affect realism and usability for AI training purposes. Furthermore, the analysis approach is based on commonly used FEM evaluation strategies in soft tissue modelling studies (Finite Element Analysis), where geometry, mesh, material properties, and boundary conditions are systematically assessed (Teixeira et al., 2023; Ismail et al., 2018; Chen et al., 2024).

### 4.2 Geometry Improvement 
The current model is based on an axisymmetric geometry generated by revolving a 2D cross-section. While computationally efficient, this approach limits anatomical realism and variation.

This project will explore improved geometry representations by:

- Modifying the base shape

- Introducing asymmetry and variation between models

- Evaluating the effect on deformation patterns

The aim is to move towards more realistic and variable breast shapes while maintaining computational feasibility. Geometry modifications will be implemented using parametric modelling techniques in Python, allowing controlled variation in breast shape and asymmetry. Similar approaches have been used in FEM studies to introduce anatomical variability while maintaining mesh compatibility (Chen et al., 2025; Teixeira et al., 2023).

### 4.3 Glandular Structure Refinement

The existing glandular representation is simplified and lacks anatomical realism. This project will improve glandular structure by:

- Implementing multiple lobular structures instead of a single region

- Introducing variation in size, shape, and spatial distribution

- Ensuring realistic glandular-to-adipose ratios

The goal is to create a more anatomically plausible internal structure while keeping the model computationally efficient. The refinement strategy is inspired by multi-component breast models, where glandular tissue is represented as distributed substructures rather than a single homogeneous region (Chen et al., 2025; Galbreath & Goswami, 2025).

### 4.4 Simulation Set-Up
Simulations will be performed using FEBio and/or Comsol.
The simulation setup includes:
• Gravity loading phase
• Dynamic motion (e.g. parabolic jump)

Outputs will include:
• Nodal displacements
• Stress distributions
• Relative volume changes

Simulation settings will remain consistent to allow fair comparison between models. This type of loading condition is commonly used to simulate realistic breast motion in biomechanical FEM studies (Chen et al., 2025).

#### 4.5 Data Extraction and Data Analysis

Simulation outputs (.vtk files) will be processed using Python.
Analysis will focus on:
• Differences in displacement patterns
• Stress distribution changes
• Sensitivity of deformation to geometry variations
• Relative differences compared to baseline model

Quantitative comparison will be performed using metrics such as displacement magnitude, spatial distribution of deformation, and stress patterns. These metrics are commonly used in FEM validation and comparison studies to assess biomechanical realism (Ismail et al., 2018).

### 4.6 Iterative Refinement

The modeling process will be iterative. Initial simulations will be performed on coarse meshes to ensure stability and feasibility. Based on observed issues (e.g. mesh quality, convergence), geometry and simulation parameters will be refined. Final simulations will be performed using improved meshes for accurate analysis.

This iterative modelling approach is frequent applied in FEM development to balance numerical stability and model realism (Ismail et al., 2018; Teixeira et al., 2023).

### 4.7. Based on Chen et al. (2024) multi-component breast FEM model

The modelling strategy in this project is inspired by multi-component finite element breast models presented in literature, such as Chen et al. (2024). In these models, the breast is represented as a combination of multiple anatomical structures, including adipose tissue, glandular tissue, pectoralis muscle, and skin, each with distinct mechanical properties.

Building upon this approach, the current project will extend an existing heterogeneous FEM model by introducing improved geometric representations and additional anatomical components. In particular, the simplified axisymmetric geometry will be replaced by a more realistic three-dimensional structure, and the internal glandular region will be refined to better reflect its anatomical organization.

Furthermore, the interaction between the breast and the thoracic wall will be improved to better capture realistic boundary conditions, as previous studies have shown that these factors significantly influence deformation behaviour (Chen et al., 2024).

- Chen, J., Sun, Y., Liu, Q., Yip, J., & Yick, K. (2024). Construction of multi-component finite element model to predict biomechanical behaviour of breasts during running and quantification of the stiffness impact of internal structure. Biomechanics and Modeling in Mechanobiology, 23(5), 1679–1694. https://doi.org/10.1007/s10237-024-01862-2

### 4.8 Model Evaluation and Validation Strategy

To assess the impact of the proposed improvements, the enhanced FEM models will be compared to the baseline model using quantitative and qualitative metrics.

Evaluation will focus on:

- Changes in displacement patterns under identical loading conditions

- Differences in stress distribution within the breast tissue

- Sensitivity of deformation to geometric and structural variations

Rather than direct clinical validation, which is outside the scope of this project, validation will be performed through comparison with expected biomechanical behaviour reported in literature. Previous studies have shown that realistic geometry, internal structure, and boundary conditions significantly influence breast deformation patterns (Chen et al., 2025; Teixeira et al., 2023; Chen et al., 2024).

All improved models will be compared against the baseline (homogeneous and) heterogeneous models developed in previous work. This approach ensures that improvements are evaluated in a consistent and reproducible manner.

## 5. Constraints, Risks and Limitations

5.1 Constraints

- Dependence on existing FEM pipeline and software (Python)

- Available computational resources

- Limited project duration (14 weeks)

### 5.2 Risks

- Mesh quality issues due to more complex geometries

- Simulation instability or convergence problems

- Increased computation time for more realistic models

### 5.3 Limitations

- No experimental or clinical validation

- Simplified anatomical representation

- Focus on model improvement rather than full system integration

## 6. Planning (14 weeks)

Phase 1 (Weeks 1–2): Literature review, define improvement strategy, analyzing the existing FEM model 
Phase 2 (Weeks 3-5): Implement geometry improvements, test initial variants
Phase 3 (Weeks 6-8): Refine glandular structure + integrate with existing model
Phase 4 (Weeks 9-10): Run FEM simulations in FEBio and/ or COMSOL
Phase 5 (Weeks 11-12): Data extraction and analysis
Phase 6 (Weeks 13-14): Write final report and prepare presentation.

Milestones:

• Week 2: Baseline model fully understood and documented
• Week 5: Improved geometry implemented
• Week 8: Glandular structure refined
• Week 10: Simulations completed
• Week 12: Analysis completed
• Week 14: Final report submitted

## 7. Expected Impact

This project improves the anatomical and biomechanical realism of an existing FEM breast model, providing a stronger foundation for simulation-based training of AI models for radiation-free breast cancer detection.

## 8. References

- Teixeira AM and Martins P (2023) A review of bioengineering techniques applied to breast tissue: Mechanical properties, tissue engineering and finite element analysis. Front. Bioeng. Biotechnol. 11:1161815. doi: 10.3389/fbioe.2023.1161815

- von Euler-Chelpin, M., Lillholm, M., Vejborg, I., Nielsen, M., & Lynge, E. (2019). Sensitivity of screening mammography by density and texture: a cohort study from a population-based screening program in Denmark. Breast cancer research: BCR, 21(1), 111. https://doi.org/10.1186/s13058-019-1203-3

- Galbreath, S., & Goswami, T. (2025). Biomechanical Behavior of Female Breast—A Review. BioMed, 5(1), 5. https://doi.org/10.3390/biomed5010005

- RIVM (2023). National evaluation of breast cancer screening in the Netherlands. https://www.rivm.nl/sites/default/files/2024-12/LETB-XV%20rapport%20English-def.pdf

- Chen, J., Sun, Y., Liu, Q., Yip, J., & Yick, K. (2024). Construction of multi-component finite element model to predict biomechanical behaviour of breasts during running and quantification of the stiffness impact of internal structure. Biomechanics and Modeling in Mechanobiology, 23(5), 1679–1694. https://doi.org/10.1007/s10237-024-01862-2

- Chen, J., Zhong, Z., Sun, Y., Yip, J., & Yick, K. (2025). Dynamic simulation of breast behaviour during different activities based on finite element modelling of multiple components of breast. Scientific Reports, 15(1), 3659. https://doi.org/10.1038/s41598-024-83598-8

- Ismail, H.M., Pretty, C.G., Signal, M.K. et al. Finite element modelling and validation for breast cancer detection using digital image elasto-tomography. Med Biol Eng Comput 56, 1715–1729 (2018). https://doi.org/10.1007/s11517-018-1804-5